Image Ambiguity Prediction Using Caption Diversity & Computer Vision

3-Month (12-Week) Detailed, Day-by-Day Execution Plan

# Overview & Scope

This project has an important structural advantage over a typical CV research plan: the ambiguity labels come from an automatic pipeline (Sentence-BERT applied to COCO's existing captions) rather than manual annotation of every image. Manual effort is needed only for the 500-image human validation subset, not the full dataset — a real time-saver that leaves more room for the full deep-learning model comparison. The scope decisions below reflect that:

- Dataset: ~2,500–3,000 COCO images (down from the original 5,000–10,000) to keep four-architecture deep-learning training feasible within 12 weeks — the labeling pipeline itself scales easily, but training compute is the real constraint.

- Deep learning models: ResNet50 and ViT-Base are the mandatory primary pair, directly testing the CNN-vs-Transformer hypothesis. EfficientNet-B0 and Swin-Tiny are explicit stretch goals in Week 8 if time allows.

- Human validation: scoped to 500 images with 2–3 volunteers, exactly as specified, since this step is what makes the automatic labeling method itself credible.

- Cross-dataset generalization: tested using a small Flickr30k subset (which also provides five captions per image), so the identical labeling pipeline can be reapplied without modification.

Each week below lists specific day-ranges with concrete tasks. Because labeling itself is largely automatic, the schedule front-loads more experimentation time in Weeks 7–10 than a comparable manually-annotated project would have.

- Phase 1 (Weeks 1–2): Literature review, scope lock, dataset collection, and caption processing

- Phase 2 (Weeks 3–4): Ambiguity score finalization and human validation

- Phase 3 (Weeks 5–6): Feature extraction and baseline models

- Phase 4 (Weeks 7–8): Deep learning models

- Phase 5 (Weeks 9–10): Explainability and experiments

- Phase 6 (Weeks 11–12): Paper writing and submission prep

# Phase 1 — Literature Review, Scope Lock & Caption Processing (Weeks 1–2)

Week 1: Literature Review & Scope Lock

| Day(s) | Task — Exactly What To Do |
| --- | --- |
| Day 1 | Search and collect papers on image ambiguity/difficulty quantification, caption-diversity or paraphrase-diversity metrics, and Sentence-BERT and sentence-embedding methods. |
| Day 2 | Collect papers on CNN-vs-Vision-Transformer comparisons, Grad-CAM/attention visualization, and the original COCO captioning dataset paper. Build a literature tracking spreadsheet (title, year, method, dataset, key finding, relevance) — target 20–25 papers. |
| Day 3 | Write up the Research Gap explicitly: most image classification research focuses on object categories, little work quantifies how ambiguous an image is to humans, and existing approaches typically require subjective manual annotation. Draft explicit hypotheses: H1 — caption-diversity-derived ambiguity labels are meaningful, as validated against human judgment; H2 — Vision Transformers outperform CNNs on ambiguity classification; H3 — combining handcrafted and deep features captures complementary signal. |
| Day 4 | Finalize scope: a dataset target of ~2,500–3,000 COCO images (down from the original 5,000–10,000), baseline models (Random Forest, XGBoost, LightGBM), a primary deep-learning pair (ResNet50, ViT-Base) with EfficientNet-B0 and Swin-Tiny as stretch goals, and a cross-dataset generalization check using a small Flickr30k subset. |
| Day 5 | Set up the Python environment (PyTorch, HuggingFace Transformers, Sentence-Transformers, OpenCV, scikit-learn, XGBoost, LightGBM) and the repository structure. Write the skeleton script for downloading COCO images and their captions. |

Deliverable: Literature tracking spreadsheet (20–25 papers); written Research Gap with explicit H1–H3 hypotheses; finalized project scope (dataset size, model list, cross-dataset plan); working environment and repo.

Week 2: Dataset Collection & Caption Processing

| Day(s) | Task — Exactly What To Do |
| --- | --- |
| Day 1 | Write a sampling script that pulls ~2,500–3,000 COCO images (stratified by supercategory for diversity), each with its five associated captions. |
| Day 2 | Run deduplication and sanity checks — confirm every sampled image has exactly five captions, and handle or discard any that don't. |
| Day 3 | Encode all captions using Sentence-BERT, producing five sentence embeddings per image. |
| Day 4 | Compute pairwise semantic similarity among the five caption embeddings per image (ten pairs) and average them. |
| Day 5 | Compute the Ambiguity Score (1 − average similarity) for every image. Inspect the score distribution to choose sensible Low/Medium/High thresholds (e.g., tertiles) and finalize the class assignment. |

Deliverable: Sampled ~2,500–3,000 COCO images with captions; Sentence-BERT caption embeddings; computed Ambiguity Scores and finalized Low/Medium/High class thresholds.

# Phase 2 — Score Finalization & Human Validation (Weeks 3–4)

Week 3: Score Sanity Check & Validation Design

| Day(s) | Task — Exactly What To Do |
| --- | --- |
| Day 1 | Sanity-check the automatically generated labels by reviewing a sample of Low, Medium, and High ambiguity images side-by-side with their captions, confirming the score behaves as expected — very similar captions should mean Low ambiguity, divergent captions should mean High. |
| Day 2 | Create a stratified 70/15/15 train/val/test split by ambiguity class, saved as manifest files reused by every later stage. |
| Day 3 | Design the human validation protocol: select 500 images (stratified across the three classes) for volunteer rating, and prepare a simple rating interface or form. |
| Day 4 | Recruit 2–3 annotators and walk them through the task: view an image without its captions and judge its ambiguity as Low/Medium/High from their own impression. |
| Day 5 | Begin the human validation rating sessions. |

Deliverable: Sanity-checked ambiguity labels; frozen train/val/test manifest files; human validation protocol designed and rating sessions underway.

Week 4: Human Validation Completion & Analysis

| Day(s) | Task — Exactly What To Do |
| --- | --- |
| Day 1–3 | Continue and complete the human validation rating sessions across all 500 selected images, spread across the recruited annotators. |
| Day 4 | Compute Cohen's Kappa between the automatically generated labels and the human-annotated labels (and inter-annotator agreement, if more than one human rated the same images), to validate the caption-diversity labeling method itself. |
| Day 5 | Write up the Human Validation section, including the Kappa results and any patterns in where automatic and human labels disagreed. |

Deliverable: Completed 500-image human validation; Cohen's Kappa (and inter-annotator agreement) computed; Human Validation section drafted.

# Phase 3 — Feature Extraction & Baseline Models (Weeks 5–6)

Week 5: Feature Extraction

| Day(s) | Task — Exactly What To Do |
| --- | --- |
| Day 1 | Extract Object Count and Relationship Density directly from COCO's existing instance annotations and object co-occurrence, minimizing new detection work. |
| Day 2 | Compute Scene Clutter (object density plus Canny edge density) and Color Entropy (Shannon entropy over the color histogram). |
| Day 3 | Run EasyOCR to compute OCR Density — the percentage of image area covered by detected text. |
| Day 4 | Consolidate all six handcrafted features into one feature table alongside the ambiguity label, and run an initial Pearson/Spearman correlation pass between each feature and the ambiguity score. |
| Day 5 | Draft the Feature Engineering section of the Methodology. |

Deliverable: Complete six-feature handcrafted table (object count, clutter, edge density, color entropy, OCR density, relationship density); initial feature-label correlation results.

Week 6: Baseline Models

| Day(s) | Task — Exactly What To Do |
| --- | --- |
| Day 1 | Train and tune Random Forest on the handcrafted feature table (grid search with cross-validation). |
| Day 2 | Train and tune XGBoost the same way. |
| Day 3 | Train and tune LightGBM the same way. |
| Day 4 | Evaluate all three baseline models on the test set: accuracy, precision, recall, F1, confusion matrix, one-vs-rest ROC-AUC, plus Spearman/Pearson correlation between predicted class and the continuous ambiguity score. |
| Day 5 | Compile the baseline comparison table (the traditional-ML experiment) and draft the Baseline Models section. |

Deliverable: Tuned Random Forest, XGBoost, and LightGBM with full test-set metrics; baseline comparison table; Baseline Models section drafted.

# Phase 4 — Deep Learning Models (Weeks 7–8)

Week 7: Primary Deep Learning Models

| Day(s) | Task — Exactly What To Do |
| --- | --- |
| Day 1 | Build the shared image-classification training pipeline: Dataset/DataLoader classes, transforms, a training loop with checkpointing, and logging. |
| Day 2 | Fine-tune ResNet50 (ImageNet-pretrained) for the three-class ambiguity problem and evaluate on the validation set. |
| Day 3 | Finish ResNet50 evaluation on the test set with the full metric suite. |
| Day 4 | Fine-tune ViT-Base/16 using the identical pipeline and splits. |
| Day 5 | Evaluate ViT-Base on the test set with the full metric suite, and compile the initial CNN-vs-Transformer comparison (the primary architecture pair). |

Deliverable: Fine-tuned ResNet50 and ViT-Base with full test-set metrics; initial CNN-vs-Transformer comparison table.

Week 8: Stretch Models & Consolidation

| Day(s) | Task — Exactly What To Do |
| --- | --- |
| Day 1 | Stretch task: fine-tune EfficientNet-B0 if on schedule. If behind, use this day as a buffer instead. |
| Day 2 | Stretch task: fine-tune Swin-Tiny if on schedule and EfficientNet-B0 is complete. If behind, continue using this day as a buffer/catch-up. |
| Day 3 | Evaluate any stretch models completed with the same metric suite as ResNet50 and ViT-Base. |
| Day 4 | Compile the full deep-learning comparison table (ResNet50, ViT-Base, and EfficientNet-B0/Swin-Tiny if attempted) and the baseline-vs-deep-learning comparison. |
| Day 5 | Draft the Deep Learning Models section of the Results. |

Deliverable: Full deep-learning comparison table (with EfficientNet-B0/Swin-Tiny if attempted); baseline-vs-deep-learning comparison; Deep Learning Models section drafted.

# Phase 5 — Explainability & Experiments (Weeks 9–10)

Week 9: Explainability & Ablation

| Day(s) | Task — Exactly What To Do |
| --- | --- |
| Day 1 | Implement Grad-CAM for ResNet50 (and EfficientNet-B0 if trained). Generate heatmaps for 2–3 representative images per ambiguity class. |
| Day 2 | Implement attention visualization for ViT (and Swin if trained). Generate attention maps for the same representative images used in Day 1, for a direct CNN-vs-Transformer explainability comparison. |
| Day 3 | Curate the clearest 8–10 explainability figures, with captions explaining which image regions drove each ambiguity prediction. |
| Day 4 | Run the feature ablation study: remove each handcrafted feature one at a time from the best baseline model, retrain, and measure the resulting performance drop to rank feature importance. |
| Day 5 | Draft the Explainability and Ablation sections. |

Deliverable: Grad-CAM and attention-visualization figures on matched images; feature ablation results; Explainability and Ablation sections drafted.

Week 10: Cross-Dataset Generalization & Final Evaluation

| Day(s) | Task — Exactly What To Do |
| --- | --- |
| Day 1 | Sample a small comparison set (~300–500 images) from Flickr30k, which also provides five captions per image, and apply the identical Sentence-BERT ambiguity-labeling pipeline to generate labels for this new dataset. |
| Day 2 | Run the best-performing trained model (from Weeks 7–8) on the Flickr30k subset without retraining, to test cross-dataset generalization. |
| Day 3 | Analyze the generalization results: compare performance on the COCO test set vs. the Flickr30k subset and discuss any domain gap. |
| Day 4 | Consolidate all final evaluation results — baseline vs. deep learning, CNN vs. Transformer, ablation, and cross-dataset generalization — into final tables and figures. |
| Day 5 | Draft the Experiments and Results sections in full, using every table and figure gathered so far. |

Deliverable: Flickr30k generalization results compared against COCO test performance; all final experiment tables and figures consolidated; Experiments and Results sections drafted.

# Phase 6 — Paper Writing & Submission Prep (Weeks 11–12)

Week 11: Full Draft (Part 1)

| Day(s) | Task — Exactly What To Do |
| --- | --- |
| Day 1 | Write the full Introduction and Related Work sections in prose, using the Week 1 literature tracking sheet. |
| Day 2 | Write the Research Gap and Dataset Construction sections, covering sourcing, sampling, and the automatic labeling method. |
| Day 3 | Write the Ambiguity Label Generation section in detail: the Sentence-BERT embedding step, pairwise similarity computation, the score formula, thresholding, and the human validation results. |
| Day 4 | Write the Methodology section: feature engineering, baseline models, deep-learning architectures, and explainability methods. |
| Day 5 | Write the Experiments and Results sections, inserting every table and figure from Weeks 6–10. |

Deliverable: Complete draft of Introduction through Results, including the detailed Ambiguity Label Generation section.

Week 12: Final Writing & Submission Prep

| Day(s) | Task — Exactly What To Do |
| --- | --- |
| Day 1 | Write the Discussion, Limitations (dataset size relative to the original 5,000–10,000 target, the two-model primary deep-learning comparison with EfficientNet/Swin as stretch-dependent, and the assumptions built into the caption-diversity labeling method), Future Work, and Conclusion sections. |
| Day 2 | Produce all remaining figures (pipeline diagram, ambiguity-score distribution, confusion matrices, ROC curves, cross-dataset generalization chart) and assemble the reference list. |
| Day 3 | Full read-through and editing pass. Format the paper to your target venue's template — ICIP, ICPR, WACV, and ACCV are typically short, IEEE-style formats with strict page limits, so check the limit early. |
| Day 4 | Prepare the thesis report and presentation slides alongside the paper, if required by your program. |
| Day 5 | Final proofreading pass, consistent reference formatting, and package the submission: paper PDF, dataset documentation, code, trained models, and data-source links. |

Deliverable: Complete paper with Discussion, Limitations, Future Work, and Conclusion; all figures finalized; thesis report and slides if required; submission-ready package.

# Risk Register & Contingencies

The most likely points where this 12-week schedule slips, and the pre-planned fallback for each:

| Risk | Contingency |
| --- | --- |
| Sentence-BERT-derived ambiguity labels might not align well with human perception | This is exactly why Weeks 3–4 include a dedicated 500-image human validation study with Cohen's Kappa. If Kappa comes out low, revisit the score formula or similarity aggregation (e.g., try a different embedding model) before treating the automatic labels as reliable ground truth for modeling. |
| Four deep-learning architectures may not all fit into the two weeks allotted (Weeks 7–8) | ResNet50 and ViT-Base are the mandatory pair that tests the core CNN-vs-Transformer hypothesis (H2). EfficientNet-B0 and Swin-Tiny are explicit stretch tasks with a clean fallback: drop them and note as future work without weakening the paper's central claim. |
| The Low/Medium/High threshold choice is somewhat arbitrary | Document the thresholding method clearly (e.g., tertiles of the score distribution) and report the continuous Spearman/Pearson correlation results as a threshold-independent complement to the classification metrics. |
| Recruiting even 2–3 volunteers for a 500-image human validation study takes real coordination time | If volunteer availability is limited, reduce the validated subset to 200–250 images rather than skipping validation entirely, and note the smaller sample size as a limitation. |
| The cross-dataset generalization check depends on Flickr30k access | If Flickr30k is unavailable, substitute another multi-caption dataset, or use a held-out COCO supercategory split as a milder cross-domain proxy, and document the substitution clearly. |
| Twelve weeks is tight given four distinct experiments (baseline vs. DL, CNN vs. Transformer, ablation, cross-dataset generalization) | If behind by Week 8, drop the cross-dataset generalization experiment (Week 10) first — it's the most self-contained and addable/droppable piece, and the other three experiments already fully support the paper's core contributions. |

# Weekly Time Budget

At roughly 20–25 hours/week, this plan is designed for a part-time research effort alongside other commitments:

- Weeks 1–2 (literature + automatic labeling pipeline): lighter than a typical CV project's early phase, since there's no manual annotation of the full dataset — a good phase to bank extra hours if you have them.

- Weeks 3–4 (human validation): moderate, but dependent on volunteer scheduling — start recruiting annotators a few days before Week 3 begins.

- Weeks 5–6 (features + baselines): light on compute, since handcrafted features and tabular models train quickly.

- Weeks 7–8 (deep learning): the heaviest compute phase — queue long training runs overnight or on a cloud GPU so they don't block your working hours.

- Weeks 9–10 (explainability + experiments): moderate — mostly running already-trained models under different conditions and generating figures.

- Weeks 11–12 (writing): steady, moderate effort — every phase above already ends with a drafted section, so this is assembly and polish.

# Target Publication Venues

As specified: ICIP, ICPR, ACCV, WACV, IEEE Access, Pattern Recognition Letters, and Expert Systems with Applications. Given the trimmed dataset size and the two-architecture primary deep-learning comparison (with the other two as schedule-dependent stretch goals), a short or workshop-track paper at one of the conference venues (ICIP, ICPR, WACV, ACCV) is a realistic first target, with the journal options (IEEE Access, Pattern Recognition Letters, Expert Systems with Applications) well suited to a fuller follow-up version with the complete four-architecture comparison and the larger original dataset target.